## Insurance_ROI
Use Case | Business Unit | Current Pain Point | AI Solution | Implementation Cost (USD) | Annual Run Cost (USD) | Annual Savings (USD) | Revenue Uplift (USD) | Feasibility | Time to Value (Months) | Strategic Impact (1-5) | ROI (%)
AI Claims Automation | Insurance Claims | Manual claims causing delays & fraud leakage | AI agent for document parsing + fraud detection | 60000 | 20000 | 100000 | 30000 | High | 3 | 5 | 62.5

## Insurance_Risk
Use Case | Risk Category | Risk Description | Likelihood | Impact | Risk Level | Mitigation Strategy | Owner | Monitoring | Status
AI Claims Automation | Fraud Detection Bias | Model may incorrectly flag genuine claims | Medium | High | High | Human-in-loop for flagged cases | Risk Head | Monthly audit | Open

## BFSI_ROI
Use Case | Business Unit | Current Pain Point | AI Solution | Implementation Cost (USD) | Annual Run Cost (USD) | Annual Savings (USD) | Revenue Uplift (USD) | Feasibility | Time to Value (Months) | Strategic Impact (1-5) | ROI (%)
AI Credit Underwriting | Retail Lending | Slow loan approvals, inconsistent decisions | AI risk scoring + decision agent | 80000 | 25000 | 120000 | 50000 | Medium | 4 | 5 | 61.9048

## BFSI_Risk
Use Case | Risk Category | Risk Description | Likelihood | Impact | Risk Level | Mitigation Strategy | Owner | Monitoring | Status
AI Credit Underwriting | Regulatory Non-compliance | Model decisions not explainable | High | High | Critical | Explainable AI + audit logs | Compliance Head | Regulatory review | Open

## Audit_ROI
Use Case | Business Unit | Current Pain Point | AI Solution | Implementation Cost (USD) | Annual Run Cost (USD) | Annual Savings (USD) | Revenue Uplift (USD) | Feasibility | Time to Value (Months) | Strategic Impact (1-5) | ROI (%)
AI Audit Assistant | Internal Audit | Manual document review is time-consuming | AI agent for control testing + anomaly detection | 40000 | 15000 | 70000 | 20000 | High | 2 | 4 | 63.6364

## Audit_Risk
Use Case | Risk Category | Risk Description | Likelihood | Impact | Risk Level | Mitigation Strategy | Owner | Monitoring | Status
AI Audit Assistant | Hallucination | AI may generate incorrect audit findings | Medium | High | High | Human validation + evidence linking | Audit Lead | Sample testing | Open