## AI_Business_Case_ROI
Use Case | Business Unit | Current Pain Point | AI Solution | Estimated Implementation Cost (USD) | Annual Operating Cost (USD) | Estimated Annual Savings (USD) | Revenue Uplift (USD) | Feasibility (High/Medium/Low) | Time to Value (Months) | Strategic Impact (1-5) | ROI (%)
Automated Claims Processing | Insurance | Manual claims review delays | AI-based document processing + decisioning agent | 50000 | 15000 | 80000 | 20000 | High | 3 | 5 | 53.8462

## Risk_Register
Use Case | Risk Category | Risk Description | Likelihood (High/Medium/Low) | Impact (High/Medium/Low) | Risk Level | Mitigation Strategy | Owner | Monitoring Mechanism | Status
Automated Claims Processing | Hallucination | AI may generate incorrect claim decisions | Medium | High | High | Human-in-the-loop validation for high-value claims | AI Governance Lead | Periodic audit of AI decisions | Open